## Main
Scrum Project
Product |  |  | Product Status
Active versions |  |  | Sponsor
Team
Scrum Master |  |  | Product Owner
Developers |  |  | Project Champion
Other Stakeholders
Projects | [5 empty] | Sprint Plan |  | Project #1
Id | Description | Start | End | Status | Remarks | Sprint | Start | End | Status | Story Points (Committed) | Story Points (Delivered) | Remarks
1 | Initial release | 2019-01-07 | 2019-03-15 | In Progress |  | Spr. 1.1 | 2019-01-07 | 2019-01-18 | Complete | 22 | 20
[6 empty] | Spr. 1.2 | 2019-01-21 | 2019-02-01 | Complete | 20 | 23
[6 empty] | Spr. 1.3 | 2019-02-04 | 2019-02-15 | Complete | 19 | 15
[6 empty] | Spr. 1.4 | 2019-02-18 | 2019-03-01 | Complete | 25 | 27
[6 empty] | Spr. 1.5 | 2019-03-04 | 2019-03-15 | In Progress | 20
Formulas:
Project #1 = [Start]+11
Start = [Project #1, row above]+3

## Backlog
Backlog
Id | Theme | As a.. | I want to .. | so that .. | Acceptance Criteria | Remarks | Priority | Status | Type | Project Id | Sprint Id | Story Points (Est.) | Effort (Actual) | Owner | Status | Remarks
DM-1 | opportunity | rep | capture opportunities with following attributes - - customer information - potential revenue - start date - end date - status | I can capture all aspects of opportunity in one place - with minimal clicks.
DM-4 | opportunity | rep | edit my own opportunities | I can update information and keep the opportunity updated through the life cycle. | Following attributes should be editable at any time: - end date Following attributes cannot be edited if status = 'Pending Approval' Opportunities belonging to others should not be editable by me.
DM-5 | opportunity | rep | view stages for my own opportunities in a single dashboard | I can measure progress and have an overall view of opportunities
DM-7 | opportunity | rep | capture companies of interest - Name Location Industry (& SIC) Type Revenue Employees Description Website Phone Fax Key contacts and contact information | I can have one system of record for potential customers | Any new company registration requires approval from area manager

## Tracker
Sprint Tracker
<- effort / day ->
Sprint Id | Backlog Id | Description | Owner | Status | Story Points (Est.) | Completed | Pending | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10
1.1 | 221 |  |  |  | 8 | 2 | 6 | 1 |  | 1
1.1 | 224 |  |  |  | 2 | 1 | 1 |  | 1
1.1 | 225 |  |  |  | 5 | 5 | 0 |  | 1 |  | 2 |  | 1 | 1
1.1 | 229 |  |  |  | 3 | 3 | 0 |  |  | 1 |  | 1 |  |  | 1
1.1 | 251 |  |  |  | 13 | 13 | 0 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
1.1 | 253 |  |  |  | 1 | 1 | 0 | [9 empty] | 1
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
|  |  |  | Total | 32 | 25 | 7 | 4 | 4 | 3 | 3 | 2 | 2 | 2 | 2 | 1 | 2
|  |  |  | Burn down |  |  |  | 28 | 24 | 21 | 18 | 16 | 14 | 12 | 10 | 9 | 7
|  |  |  | Burn up |  |  |  | 4 | 8 | 11 | 14 | 16 | 18 | 20 | 22 | 23 | 25

## Impediment
Impediments
Id | Description | Raised By | Raised On | Sprint # | Impacted Backlog # | Owner | Status | Resolution | Resolved On | Remarks

## Retrospective
Retrospective Log
Sprint # | Date | Owner | Continue Doing | Start Doing | Stop Doing | Remarks

## Summary
Reports & Dashboards
Sprint Velocity
Burn down Chart | Burn up Chart

## References
References
External |  | Internal
Description | Link | Description | Link
Glossary & Terminology | https://www.scrumalliance.org/community/articles/2007/march/glossary-of-scrum-terms